## Sheet1
Sprint #1 Burndown Chart
Duration: 2 days
Task ID | User Story | Initial Estimate(Hours) | 2025-06-21 | 2025-06-22
|  | Day 0 | Day 1 | Day 2
1 | Plan Project Scope and Sprint Timeline | 0.5 | 0.5 | 0
2 | Define Project User Stories | 0.5 | 0.5 | 0
3 | Create Burndown Chart Template | 0.5 | 0 | 0.5
4 | Finalize Agile Process Report | 1 | 0 | 1
Remaining Effort |  | 2.5 | 1.5 | 0
Ideal Trend |  | 2.5 | 1.25 | 0
Sprint #2 Burndown Chart
Duration: 5 days
Task ID | User Story | Initial Estimate(Hours) | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | Create Github Repository | 0.5 | 0.5 | 0 | 0 | 0 | 0
2 | Build Micro:bit Robot | 0.5 | 0.5 | 0 | 0 | 0 | 0
3 | Display Images on Led Matrix | 1.5 | 1.5 | 0 | 0 | 0 | 0
4 | Recognize Different Faces | 1 | 0 | 1 | 0 | 0 | 0
5 | Link Faces with Related Numbers | 1 | 0 | 1 | 0 | 0 | 0
6 | Hash Recognized Faces | 2 | 0 | 0.5 | 1.5 | 0 | 0
7 | Add Error Handling | 1 | 0 | 0 | 1 | 0 | 0
8 | Finish Burndown Chart | 0.5 | 0 | 0 | 0 | 0.5 | 0
9 | Manage Code Version Control | 0.5 | 0 | 0 | 0 | 0.5 | 0
10 | Compile Final Report | 3.5 | 0 | 0 | 0 | 1 | 2.5
11 | Record Project Demo Video | 2 | 0 | 0 | 0 | 0 | 2
Remaining Effort |  | 14 | 11.5 | 9 | 6.5 | 4.5 | 0
Ideal Trend |  | 14 | 11.2 | 8.4 | 5.6 | 2.8 | 0